## Project
|  |  |  | Date Created: | 2018-01-14 |  |  | 2017-12-01 | [30 empty] | 2018-01-01 | [30 empty] | 2018-02-01
| ** Project |  |  | Last Update: | 2018-01-14 09:26 |  |  |  | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off | [5 empty] | Off | Off
No | Task | Person in Charge | Period (days) | Start Date | Finish Date | Progress | Status | time axis 2017-12-01 to 2018-02-28
 | time axis 2017-12-01 to 2018-02-28
1 | 统一权限登录管理 | 王艺峰，陆遥 |  | 2017-11-01 | 2018-01-12 | 80%
2 | 审批系统页面事件日志框架 | 王剑 |  | 2017-11-01 | 2018-01-05 | 100%
3 | 数据调用中心 | 王艺峰 |  | 2017-11-13 | 2018-01-04 | 90%
4 | 环境及部署 | 王艺峰 |  | 2017-11-13 | 2018-01-05 | 80%
5 | 审批系统流程修改 | 王剑 |  | 2017-11-10 |  | 50%
6 | ACTIVITI服务抽取成独立服务 | 王剑 |  | 2017-12-21 | 2018-01-26 | 30%
7 | 审批系统20171130版 修改 | 徐璟煜 |  | 2017-12-06 | 2018-01-04 | 100%
8 | 其他工作 | 徐璟煜 |  | 2017-12-18 | 2018-01-16 | 90%
1 | 统一权限登录管理 | 王艺峰
2 | 需求分析 | 王艺峰，王剑 |  | 2017-11-01 | 2017-11-01 | 100%
3 | 功能设计 | 王艺峰，陆遥 |  | 2017-11-01 | 2017-11-01 | 100%
4 | 开发框架搭建 | 陆遥，吴超 |  | 2017-11-01 | 2017-11-01 | 100%
5 | 功能开发 | 陆遥 |  | 2017-11-01 | 2017-11-10 | 100%
6 | 整体流程demo开发 | 陆遥 |  | 2017-11-11 | 2017-11-21 | 100%
7 | 测试环境部署调试 | 陆遥 |  | 2017-11-22 | 2017-11-27 | 100%
8 | UAT环境部署 | 陆遥 |  | 2018-01-01 | 2018-01-12 | 20% | Behind | bar: 2018-01-01 to 2018-01-12
9
10 | 审批系统页面事件日志框架 | 王剑
11 | 需求分析 | 王剑 |  | 2017-11-01 | 2017-11-01 | 100%
12 | 功能设计 | 王剑 |  | 2017-11-01 | 2017-11-01 | 100%
13 | demo验证 | 王剑 |  | 2017-11-01 | 2017-11-01 | 100%
14 | 开发
15 | 注册登录日志开发 | 王剑 |  | 2017-11-01 | 2017-11-03 | 100%
16 | 渠道管理 | 陈睿 |  | 2017-11-15 | 2017-12-01 | 100% | Completed | bar: 2017-12-01
17 | 电话审核 | 张浩 |  | 2017-11-15 | 2017-11-21 | 100%
18 | 资料审核 | 张浩 |  | 2017-11-21 | 2017-11-30 | 100%
19 | 门店登记 | 张浩 |  | 2017-12-01 | 2017-12-05 | 100% | Completed | bar: 2017-12-01 to 2017-12-05
20 | 面签审核 | 张浩 |  | 2017-12-05 | 2017-12-08 | 100% | Completed | bar: 2017-12-05 to 2017-12-08
21 | 测试
22 | 单模块测试 | 徐琰 |  | 2017-12-25 | 2017-12-29 | 100% | Completed | bar: 2017-12-25 to 2017-12-29
23 | 全模块测试 | 徐琰 |  | 2018-01-02 | 2018-01-05 | 100% | Completed | bar: 2018-01-02 to 2018-01-05
24 | UAT测试（风控组检测） |  |  | 2018-01-08 | 2018-01-09 | 100% | Completed | bar: 2018-01-08 to 2018-01-09
25
26 | 数据调用中心
27 | 问卷库（DecisionService接口，对接胡兆宇）
28 | 审批系统对接电核本人接口 |  |  | 2018-01-08 | 2018-01-09 | 100% | Completed | bar: 2018-01-08 to 2018-01-09
29 | 审批系统对接电核联系人接口 |  |  | 2018-01-10 | 2018-01-12 | 100% | Completed | bar: 2018-01-10 to 2018-01-12
| UAT测试部署 |  |  | 2018-01-15 | 2018-01-19 |  | Not started | bar: 2018-01-15 to 2018-01-19
31
32 | 环境及部署
33 | devops
34 | 调查gitlab pipline | 王艺峰 |  | 2017-11-13 | 2017-11-17 | 100%
35 | 审批系统前端（ci+cd，uat环境） | 王艺峰 |  | 2018-01-22 | 2018-01-24 | 90% | In-progress | bar: 2018-01-22 to 2018-01-24
36 | 审批系统管理端（ci+cd，uat环境） | 王艺峰 |  | 2018-01-10 | 2018-01-12 | 100% | Completed | bar: 2018-01-10 to 2018-01-12
37 | 其他一些应用（ci+cd，uat环境） | 王艺峰 |  | 2018-01-15 | 2018-01-19 | 100% | Completed | bar: 2018-01-15 to 2018-01-19
38 | 审批系统前端maven化
39
40 | 审批系统流程修改（对接熊文静）
41 | snippetBPMN协议定义 |  |  | 2017-11-10 | 2017-11-15 | 100%
42 | 审批流程各节点名称统一 |  |  | 2017-11-20 | 2017-11-30 | 100%
43 | 开发
44
45 | ACTIVITI服务抽取成独立服务
46 | ACTIVITI抽离 |  |  | 2017-12-21 | 2018-01-19 | 40% | In-progress | bar: 2017-12-21 to 2018-01-19
47 | 审批系统对应修改 |  |  | 2018-01-19 | 2018-01-26 |  | Not started | bar: 2018-01-19 to 2018-01-26
48
49 | 审批系统20171130版 修改
50 | 需求分析 | 王剑 |  | 2017-12-06 | 2017-12-09 | 100% | Completed | bar: 2017-12-06 to 2017-12-09
51 | 审批系统前端
52 | 渠道管理 | 陈睿 |  | 2017-12-11 | 2017-12-19 | 100% | Completed | bar: 2017-12-11 to 2017-12-19
53 | 资料审核 | 陈睿 |  | 2017-12-11 | 2017-12-21 | 100% | Completed | bar: 2017-12-11 to 2017-12-21
54 | 资料管理-前台 | 吴超
55 | 资料管理-后台 | 吴超 |  | 2017-12-25 | 2017-12-29 | 100% | Completed | bar: 2017-12-25 to 2017-12-29
56 | 审批系统管理端
57 | “资料审核”管理 | 吴超 |  | 2017-12-11 | 2017-12-28 | 100% | Completed | bar: 2017-12-11 to 2017-12-28
58 | 贷款信息（审批+银数）数据管理 | 陈睿 |  | 2017-12-11 | 2017-12-29 | 100% | Completed | bar: 2017-12-11 to 2017-12-29
59 | UAT发布及测试 |  |  | 2017-12-29 | 2018-01-04 | 100% | Completed | bar: 2017-12-29 to 2018-01-04
60
61 | 其他工作
62 | 工位号及用户设置需求修改（陈立刚） | 李彬
63 | 需求分析 |  |  | 2017-12-27 | 2017-12-28 | 100% | Completed | bar: 2017-12-27 to 2017-12-28
64 | 工位号相关功能修改 |  |  | 2017-12-29 | 2018-01-02 | 100% | Completed | bar: 2017-12-29 to 2018-01-02
65 | 用户相关功能修改 |  |  | 2018-01-03 | 2018-01-04 | 100% | Completed | bar: 2018-01-03 to 2018-01-04
66 | UAT发布及测试 |  |  | 2018-01-04 | 2018-01-08 | 100% | Completed | bar: 2018-01-04 to 2018-01-08
67 | 审批系统日常维护不予登录（沈东良）
68 | 维护时间在配置文件中维护（暂定，19:00-次日8:00） |  |  | 2018-01-02 | 2018-01-05 | 100% | Completed | bar: 2018-01-02 to 2018-01-05
69 | 开发 |  |  | 2018-01-02 | 2018-01-05 | 100% | Completed | bar: 2018-01-02 to 2018-01-05
70 | UAT发布及测试 |  |  | 2018-01-08 | 2018-01-09 | 100% | Completed | bar: 2018-01-08 to 2018-01-09
71 | 面签工位监控（图像采集程序优化，陈立刚）
72 | 界面上删去对摄像头设置的选择 |  |  | 2018-01-05 | 2018-01-09 | 100% | Completed | bar: 2018-01-05 to 2018-01-09
73 | 对摄像头的设置写死在配置文件里 |  |  | 2018-01-05 | 2018-01-09 | 100% | Completed | bar: 2018-01-05 to 2018-01-09
74 | 自动化合格件定时任务（姚伟） |  |  | 2018-01-12 | 2018-01-16 | 50% | In-progress | bar: 2018-01-12 to 2018-01-16
75